## Stakeholders
Stakeholder ID | Name/Group | Role | Interest | Influence | Key Concerns | Source File(s) | Supporting Quote/Evidence | Evidence Status
SH-01 | Ingrid Solheim | Founder, owner (daglig leder) and product owner | Stop losing inquiries; self-service menus and booking; kitchen overview; deposit; keep Fiken; show food origin; live by 2027-03-01 | High | Lost inquiries (about 60 000 NOK); no-shows at weddings; budget about 450 000 NOK; deadline | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | 01_interview_owner_2026-08-14.txt [header]: "Ingrid Solheim (founder and owner, Ekte Mat AS)" 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 5]: "Ingrid acts as product owner; available Tuesdays 09-10" Note: Influence High: owner and appointed product owner (documented). | DIRECT
SH-02 | Sunniva Berg | Event coordinator | One order record instead of Excel + printouts; capacity calendar; automatic 7-day reminders; allergy confirmation | Medium | Forgotten updates; slow replies in peak season; overbooking; corporate customers lost if deposit is forced | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt | 01_interview_event-coordinator_2026-08-15.txt [header]: "Sunniva Berg (event coordinator, Ekte Mat AS)" 01_interview_event-coordinator_2026-08-15.txt [Q3]: "If we force a deposit on them, we will lose them." Note: Influence Medium is an assessment: key daily user, no documented decision authority. | ASSUMPTION
SH-03 | Mateo Rinaldi | Head chef | Kitchen wall-tablet overview; PIN login; edit seasonal menus; supplier-linked ingredients; prep list; offline access | Medium | Allergy visibility; speed; internet outages | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [header]: "Mateo Rinaldi (head chef)" 01_interview_head-chef_2026-08-15.txt [Q1]: "One screen in the kitchen. Tablet on the wall." Note: Influence Medium is an assessment: owns kitchen operations, no documented project authority. | ASSUMPTION
SH-04 | Henrik Aas (Fjordtek AS) | Office manager at Ekte Mat's biggest corporate customer | Company login; standing orders; copy orders; change until 10:00 day before; approval above 15 000 NOK; monthly EHF invoice | Medium | Late confirmations; no prepayment allowed; EU/EEA data storage; deletion of employee names | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 01_Requirements/sources/01_interview_owner_2026-08-14.txt | 01_interview_corporate-customer_2026-08-19.txt [header]: "Henrik Aas (office manager, Fjordtek AS - fictional company, 180 employees)" 01_interview_owner_2026-08-14.txt [Q6]: "maybe Fjordtek - they are our biggest corporate customer." Note: Influence Medium is an assessment based on 'biggest corporate customer'. | ASSUMPTION
SH-05 | Fjordtek IT department | IT function of a corporate customer (not interviewed) | Data location and deletion | Low | Data stored in EU/EEA; employee names deleted at end of relationship | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_corporate-customer_2026-08-19.txt [Q4]: "Our IT department will ask where our data is stored." Note: Group named only indirectly; influence assessed. | ASSUMPTION
SH-06 | Fjordtek finance department | Finance function of a corporate customer (not interviewed) | Invoice-based payment | Low | Prepayment not allowed | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_corporate-customer_2026-08-19.txt [Q3]: "We cannot prepay, our finance department does not allow it." Note: Group named only indirectly; influence assessed. | ASSUMPTION
SH-07 | Corporate customers (group) | Customer segment: weekly lunches and meetings | Recurring orders, several orderers, EHF invoicing with references, English menus | Medium | PDF invoices rejected; repetitive weekly e-mails; reorder without details | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 3]: "Customer groups: corporate (weekly lunches, meetings), private (parties), weddings, health-conscious" 04_dataset_customer-emails_2026-10-20.csv [E004]: "our finance department only accepts EHF invoices with our PO number." 04_dataset_customer-emails_2026-10-20.csv [E007]: "It is a pain to e-mail every week." Note: Segment documented; influence assessed. | ASSUMPTION
SH-08 | Private customers (parties) | Customer segment: parties, birthdays, confirmations | Vipps payment, e-mail receipt, pick-up option, phone ordering | Low | Payment method; ability to order without internet | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 3]: "private (parties)" 04_dataset_customer-emails_2026-10-20.csv [E009]: "Kan jeg betale med Vipps for bursdag 30 pers?" [translation: Can I pay with Vipps for a birthday party of 30?] 04_dataset_customer-emails_2026-10-20.csv [E024]: "Kan jeg fortsatt bestille på telefon?" [translation: Can I still order by phone?] Note: Segment documented; influence assessed. | ASSUMPTION
SH-09 | Wedding customers | Customer segment: weddings (season from May 2027) | Capacity for served dinners; deposit amount | Low | Availability on the date; deposit terms | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_owner_2026-08-14.txt [Q2]: "We have had too many no-shows at weddings." 04_dataset_customer-emails_2026-10-20.csv [E005]: "Har dere kapasitet? Hvor mye må vi betale i depositum?" [translation: Do you have capacity? How much do we have to pay as a deposit?] Note: Segment documented; influence assessed. | ASSUMPTION
SH-10 | Health-conscious customers | Customer segment named at kick-off | Not documented beyond the segment name | Low | Not documented (no interview or e-mail attributable) | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 3]: "health-conscious" Note: Only the segment name is evidenced; concerns unknown. | ASSUMPTION
SH-11 | Driver (name not documented) | Delivers orders (not interviewed) | Not documented | Low | Currently gets the address from a printout and uses own phone | 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 03_Architecture/03_landscape_current-it_2026-10-20.txt | 02_process_as-is-order-handling_2026-08-15.md [step 10]: "Kitchen prepares, driver delivers. Driver gets the address from the printout." 03_landscape_current-it_2026-10-20.txt [Driver]: "Driver: own phone, Google Maps" Note: Role evidenced; needs not elicited (see issue register). | ASSUMPTION
SH-12 | Data-protection consultant (name not documented) | External data-protection adviser | GDPR obligations | Medium | Health data, retention, data-subject rights, data processing agreements | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [header]: "Note from data-protection consultant (phone call, 20 Aug 2026)" Note: Advisory role; influence assessed. | ASSUMPTION
SH-13 | Student project team | Three student developers, 2-week sprints | Deliver first version by go-live | Medium | Budget, deadline, scope | 00_Project_management/00_plan_budget-and-constraints_2026-10-20.txt | 00_plan_budget-and-constraints_2026-10-20.txt [Team]: "Team: 3 student developers, 2-week sprints, product owner Ingrid (Tue 09-10)" Note: Influence assessed: delivers the system but does not own scope. | ASSUMPTION
SH-14 | Suppliers (farms, boats) | Ingredient suppliers whose origin is shown | Being shown as origin; becoming a supplier | Low | Not elicited | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_owner_2026-08-14.txt [Q4]: "where the lamb or the fish comes from - the farm, the boat." 01_interview_head-chef_2026-08-15.txt [Q2]: "ingredients should be linked to suppliers" 04_dataset_customer-emails_2026-10-20.csv [E025]: "we are an organic vegetable farm in Hardanger and would like to become a supplier." Note: Group evidenced; influence assessed. | ASSUMPTION

## User stories
Story ID | Epic ID | Epic Name | User Story | Acceptance Criteria (2–3) | MoSCoW Priority | One-line Priority Rationale | Source File(s) | Supporting Quote | Evidence Status | Assumptions/Dependencies
US-01 | EP-01 | Online menus and booking requests | As a prospective customer, I want to see current menus and prices online at any time so that I can plan an event without e-mailing for a quote. | AC1: Given a published menu, when a visitor opens the menu page, then each dish is shown with its price in NOK. AC2: Given it is outside office hours, 8.00 to 17.00, when a visitor opens the website, then menus and prices are available without contacting staff. | Must | Named by the owner as a first function; core of the documented project goal. | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | 01_interview_owner_2026-08-14.txt [Q2]: "Customers must be able to see our menus and prices and send a booking request themselves, at any hour." 04_dataset_customer-emails_2026-10-20.csv [E001]: "Can you send the menu and price?" 04_dataset_customer-emails_2026-10-20.csv [E015]: "Can you send a price list PDF?" 01_vision_draft-v0.3_2026-10-20.docx [para 1]: "lets customers see menus, prices and food origin" | DIRECT | Pricing unit (per person, as in the autumn menu draft) assumed for all packages; VAT display and minimum order not documented.
US-02 | EP-01 | Online menus and booking requests | As a prospective customer, I want to send a booking request online at any hour so that my request is registered and not lost. | AC1: Given a visitor has completed the booking form, when they submit it, then the request is stored and listed for the coordinator. AC2: Given the submission cannot be stored, when the visitor submits, then an error message is shown to the visitor. | Must | Lost inquiries are the main documented problem; replaces e-mail intake (kick-off goal). | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_owner_2026-08-14.txt [Q1]: "We lose inquiries. Last December we found three julebord requests in the spam folder after the date had passed." 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 1]: "Goal: replace e-mail/phone/Excel ordering with an online ordering and event booking system" 04_dataset_customer-emails_2026-10-20.csv [E023]: "I tried the contact form on your website three times and got an error." 04_dataset_customer-emails_2026-10-20.csv [E006]: "We have booked another caterer now." | DIRECT | Required booking fields are not defined. Whether a request is auto-confirmed or reviewed by the coordinator is not decided.
US-03 | EP-01 | Online menus and booking requests | As a prospective customer, I want to see which dates are available so that I only request dates Ekte Mat can serve. | AC1: Given a date has reached the capacity limit, when a customer views the availability calendar, then the date is shown as unavailable. AC2: Given a date has remaining capacity, when a customer views the calendar, then the date can be selected for a request. | Should | Clear customer need, but booking requests can be handled without it at go-live. | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E001]: "Is it possible to see online which dates are free?" 04_dataset_customer-emails_2026-10-20.csv [E005]: "Har dere kapasitet?" [translation: Do you have capacity?] | DIRECT | Depends on US-10 and the capacity rule (ISS-06). Whether exact remaining capacity is shown publicly is not decided.
US-04 | EP-01 | Online menus and booking requests | As a customer, I want an automatic confirmation and a visible status for my order so that I know whether it is accepted. | AC1: Given a booking request is stored, when submission completes, then the customer receives a message that the request was received. AC2: Given the coordinator confirms the order, when the status changes, then the customer is notified that the order is confirmed. | Should | Strongly evidenced pain point, but not named as a go-live condition. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_corporate-customer_2026-08-19.txt [Q1]: "Then I wait for a confirmation. Sometimes it arrives Monday morning, which is too late for me." 04_dataset_customer-emails_2026-10-20.csv [E011]: "Is our order for tomorrow confirmed? We never got a confirmation e-mail." | DIRECT | PO REVIEW: priority could be Must because it is closely tied to the lost-inquiry problem. Notification channel (e-mail) is an ASSUMPTION.
US-05 | EP-01 | Online menus and booking requests | As a customer, I want menus to show where key ingredients come from (farm or boat) so that I can choose food with a known origin. | AC1: Given a dish has an ingredient linked to a supplier, when a customer views the menu, then the origin of that ingredient is shown. [Only one AC is supported by the evidence; further criteria need PO input.] | Should | Part of the vision and brand, but stated by the owner as a wish ('would love'). | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | 01_interview_owner_2026-08-14.txt [Q4]: "I would love every menu to show where the lamb or the fish comes from - the farm, the boat." 04_dataset_customer-emails_2026-10-20.csv [E008]: "Which farm is the lamb from?" 01_vision_draft-v0.3_2026-10-20.docx [para 1]: "see menus, prices and food origin" | DIRECT | Depends on US-19. Which ingredients must show origin ('every menu' vs key ingredients) is not defined. Only one AC is supported by evidence.
US-06 | EP-01 | Online menus and booking requests | As a customer, I want the allergens in each dish to be clearly marked so that guests with allergies can choose safely. | AC1: Given a dish contains an allergen on the labelling list, when the menu is displayed, then that allergen is shown for the dish. AC2: Given the English version of the menu, when it is displayed, then the same allergen markings are shown. | Should | Safety-relevant and requested; no source states it as a go-live condition. | 04_Data/04_reference_lunch-menu-autumn_2026-10-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_reference_lunch-menu-autumn_2026-10-20.txt [last line]: "Allergens to be labelled: fish, milk, gluten, nuts, celery, mustard." 04_dataset_customer-emails_2026-10-20.csv [E012]: "Is your menu available in English with allergens marked?" 04_dataset_customer-emails_2026-10-20.csv [E019]: "Please label gluten-free items clearly on the buffet." | DIRECT | PO REVIEW: consider Must. Legal allergen-labelling obligations are not in the evidence. E019 concerns physical buffet labels, so applying it to the online menu is INFERRED. Depends on NFR-10.
US-07 | EP-01 | Online menus and booking requests | As a customer, I want to record allergies and diets per guest group in my order so that the kitchen can prepare safe meals. | AC1: Given an order, when the customer adds a guest group, then they can enter the number of guests and their allergies or diets for that group. AC2: Given allergy information is entered, when the order is saved, then no guest name is required for the allergy data. | Must | Documented as mandatory for every order; safety incident in 2024; GDPR advice on health data. | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_event-coordinator_2026-08-15.txt [Q5]: "Every order has to show allergies and diets per guest group" 01_note_gdpr-consultant_2026-08-20.txt [bullet 1]: "Store per guest group, not per named guest, unless strictly needed." 04_dataset_customer-emails_2026-10-20.csv [E002]: "To av gjestene har nøtteallergi og en er cøliaki." [translation: Two of the guests have a nut allergy and one has coeliac disease.] 04_dataset_customer-emails_2026-10-20.csv [E022]: "Adding one guest with shellfish allergy to the order for tonight." | DIRECT | Standard list of allergens/diets: the menu draft lists six allergens; whether the order form uses the same list is not decided.
US-08 | EP-01 | Online menus and booking requests | As a corporate customer, I want to see the share of local ingredients per order so that I can use it in sustainability (ESG) reporting. | AC1: Given an order whose dishes have ingredients with recorded origin, when the customer views the order, then the share of local ingredients is shown. [Only one AC is supported by the evidence; further criteria need PO input.] | Could | Single customer request; not linked to go-live needs. | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E021]: "can you tell us the CO2 footprint or at least the share of local ingredients per order?" | DIRECT | Definition of 'local' and the calculation basis (weight, cost, count) are missing. Depends on US-19. CO2 footprint not included (no data source).
US-09 | EP-02 | Order management and event coordination | As the event coordinator, I want to register and manage all orders, including orders received by phone or e-mail, in one system so that I no longer keep Excel and printouts in sync. | AC1: Given an order received by phone, when the coordinator registers it, then it appears in the same order list as online orders. AC2: Given the coordinator changes an order, when the change is saved, then the kitchen overview shows the updated order without re-printing. | Must | Replacing e-mail/phone/Excel ordering is the documented project goal. | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 04_Data/04_dataset_customer-emails_2026-10-20.csv 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | 01_interview_event-coordinator_2026-08-15.txt [Q1]: "I have to remember to update both the sheet and the printout. Sometimes I forget." 02_process_as-is-order-handling_2026-08-15.md [step 1]: "Customer sends an e-mail or calls (phone calls are noted on paper)." 04_dataset_customer-emails_2026-10-20.csv [E024]: "Kan jeg fortsatt bestille på telefon?" [translation: Can I still order by phone?] 01_vision_draft-v0.3_2026-10-20.docx [para 1]: "it gives the kitchen one reliable overview of every order and allergy." | DIRECT | Assumes phone remains an order channel (ISS-12). Migration of existing Excel orders is not addressed.
US-10 | EP-02 | Order management and event coordination | As the event coordinator, I want a calendar showing booked guests per day against kitchen capacity so that I do not overbook. | AC1: Given confirmed orders on a date, when the coordinator opens the calendar, then the total number of guests for that date is shown. AC2: Given the booked guests for a date exceed the capacity limit, when the calendar is shown, then the date is flagged as over capacity. | Should | Clear operational need; booking requests are still reviewed manually. | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | 01_interview_event-coordinator_2026-08-15.txt [Q4]: "A calendar that shows how many guests we already have per day, so I do not overbook. Our kitchen can do about 400 covers a day, 250 if there is a wedding with a served dinner." 02_process_as-is-order-handling_2026-08-15.md [step 3]: "If the day is "full" (gut feeling), she proposes another date." | DIRECT | PO REVIEW: becomes Must if online requests are confirmed automatically. Capacity values are approximate ('about'): see ISS-06.
US-11 | EP-02 | Order management and event coordination | As a customer, I want to change the number of guests and allergy information for my order online so that changes reach Ekte Mat without phone calls. | AC1: Given an existing order before the change deadline, when the customer changes the number of guests, then the order shows the new number for the coordinator and the kitchen. AC2: Given a customer adds a guest group with an allergy, when the change is saved, then the kitchen overview shows the allergy for that order. | Should | Frequent pain point; not documented as a go-live condition. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "change the number of people until 10:00 the day before" 04_dataset_customer-emails_2026-10-20.csv [E003]: "we need to change from 40 to 55 guests for our event next Thursday. I called yesterday but nobody picked up." 02_process_as-is-order-handling_2026-08-15.md [step 8]: "Changes (guest count, allergies) arrive by phone/e-mail" 01_vision_draft-v0.3_2026-10-20.docx [para 1]: "book and change orders any time" | DIRECT | The change deadline is not agreed: 10:00 the day before is one customer's wish, while the vision says 'any time' (ISS-03).
US-12 | EP-02 | Order management and event coordination | As the event coordinator, I want customers to get an automatic reminder seven days before the event to confirm final guest numbers so that I do not have to phone everyone. | AC1: Given an event is seven days away, when the daily reminder job runs, then the customer receives a reminder to confirm final guest numbers. AC2: Given a reminder has been sent, when the coordinator opens the order, then the order shows that the reminder was sent. | Should | Reduces manual work; current manual step exists as a fallback. | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | 01_interview_event-coordinator_2026-08-15.txt [Q4]: "automatic reminders to customers about final guest numbers seven days before the event." 02_process_as-is-order-handling_2026-08-15.md [step 9]: "7 days before the event the coordinator phones the customer to confirm final numbers (if she has time)." | DIRECT | Reminder channel and what happens if the customer does not respond are not documented.
US-13 | EP-02 | Order management and event coordination | As a customer, I want to request cancellation of an order so that Ekte Mat is informed in time. | AC1: Given an existing order, when the customer requests cancellation, then the order status shows 'cancellation requested' and the coordinator is notified. [Only one AC is supported by the evidence; further criteria need PO input.] | Could | Single request; cancellation terms are undefined. | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E013]: "Unfortunately we have to cancel the dinner on 3 October" | UNRESOLVED | Cancellation terms and fees are missing (ISS-04). The AC is an ASSUMPTION about the mechanism.
US-14 | EP-02 | Order management and event coordination | As a customer, I want to choose pick-up or delivery and state the delivery time so that the food arrives when and where I need it. | AC1: Given a customer selects delivery, when they submit the order, then a delivery address and a requested delivery time are required. AC2: Given a customer selects pick-up, when they submit the order, then no delivery address is required. | Should | Needed for fulfilment, but can be handled through notes at go-live. | 04_Data/04_dataset_customer-emails_2026-10-20.csv 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | 04_dataset_customer-emails_2026-10-20.csv [E014]: "Kan vi hente maten selv i stedet for levering?" [translation: Can we collect the food ourselves instead of having it delivered?] 04_dataset_customer-emails_2026-10-20.csv [E018]: "Can you deliver between 10:45 and 11:00 exactly?" 02_process_as-is-order-handling_2026-08-15.md [step 10]: "Driver gets the address from the printout." | DIRECT | Delivery area, fees and time-window precision are not documented. Driver needs are not elicited (ISS-13).
US-15 | EP-03 | Kitchen operations | As the head chef, I want a daily overview on a kitchen wall tablet showing orders, portions per dish and allergies in red so that the kitchen prepares the right food safely. | AC1: Given confirmed orders for a day, when the chef opens the day view, then each order and the total portions of each dish are shown. AC2: Given an order contains allergy or diet information, when it is displayed, then that information is shown in red. | Must | The owner and the vision require a kitchen order overview; it replaces printouts. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt 01_Requirements/sources/01_interview_owner_2026-08-14.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_head-chef_2026-08-15.txt [Q1]: "For each day: which orders, how many portions of each dish, allergies in red." 01_interview_owner_2026-08-14.txt [Q2]: "I want a proper order overview for the kitchen" 02_process_as-is-order-handling_2026-08-15.md [step 7]: "Coordinator prints the order and pins it on the kitchen board." 04_dataset_customer-emails_2026-10-20.csv [E017]: "The note said 'V x4' but nothing came." | DIRECT | Depends on NFR-03 (offline) and NFR-13 (device). E017 supports clear diet visibility (INFERRED).
US-16 | EP-03 | Kitchen operations | As the event coordinator, I want the kitchen to confirm that it has seen each order's allergy information so that allergies are not missed. | AC1: Given an order with allergy information, when a kitchen user confirms it, then the confirmation is recorded with time and user. AC2: Given an order's allergy information has not been confirmed, when the coordinator views the order, then it is marked as unconfirmed. | Must | Stated as mandatory after a near-miss nut incident in 2024; customers ask for this assurance. | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_event-coordinator_2026-08-15.txt [Q5]: "the kitchen must confirm they have seen it. We had a nut incident in 2024 - nobody was hurt, but it was close." 04_dataset_customer-emails_2026-10-20.csv [E002]: "Kan dere bekrefte at kjøkkenet har fått beskjed?" [translation: Can you confirm that the kitchen has been informed?] | DIRECT | PO REVIEW: Must is based on safety evidence, not on a stated go-live condition. Whether a later allergy change resets the confirmation is an ASSUMPTION to confirm.
US-17 | EP-03 | Kitchen operations | As a kitchen staff member, I want to log in to the kitchen tablet with a PIN so that I can use it quickly while working. | AC1: Given the kitchen tablet, when a user enters a valid PIN, then the kitchen view opens. AC2: Given an invalid PIN is entered, when the user submits it, then access is denied. | Should | Usability need for the kitchen view; not a go-live condition on its own. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q1]: "I do not want to log in with long passwords with flour on my hands - a PIN is fine." | DIRECT | PIN length, lock-out rules and the security of health data access are not documented (ISS-14).
US-18 | EP-03 | Kitchen operations | As the head chef, I want to edit the menu myself so that seasonal changes are published without help. | AC1: Given the chef is logged in with menu rights, when he changes a dish and saves, then the published menu shows the change. [Only one AC is supported by the evidence; further criteria need PO input.] | Should | Menus change four times a year; the first change can be handled by the team. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt 03_Architecture/03_landscape_current-it_2026-10-20.txt | 01_interview_head-chef_2026-08-15.txt [Q2]: "Menus change with the season, four times a year. I want to edit the menu myself" 03_landscape_current-it_2026-10-20.txt [Constraints]: "nobody technical in-house" | DIRECT | Who may change prices is not documented. Related to NFR-12.
US-19 | EP-03 | Kitchen operations | As the head chef, I want ingredients to be linked to suppliers so that dish origin can be shown to customers. | AC1: Given a supplier is registered, when the chef links an ingredient to it, then dishes using that ingredient show the supplier as origin. [Only one AC is supported by the evidence; further criteria need PO input.] | Should | Enables US-05 (Should); not a go-live condition. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q2]: "ingredients should be linked to suppliers, so we can show origin like Ingrid wants." | DIRECT | Supplier data fields are not defined.
US-20 | EP-03 | Kitchen operations | As the head chef, I want a prep list with total kilos of each ingredient for the next three days so that I can plan purchasing and preparation. | AC1: Given confirmed orders for the next three days, when the chef opens the prep list, then the total kilos of each ingredient are shown. [Only one AC is supported by the evidence; further criteria need PO input.] | Could | Useful, but depends on recipe quantity data that does not exist in the evidence. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q2]: "I need a prep list: total kilos of each ingredient for the next three days." | DIRECT | Requires ingredient quantities per portion (missing evidence, ISS-15).
US-21 | EP-04 | Payments and invoicing | As a private customer, I want to pay with Vipps and get a receipt by e-mail so that payment is easy and documented. | AC1: Given a private customer's order, when they choose to pay, then Vipps is offered as a payment method. AC2: Given a Vipps payment is completed, when the order is updated, then it is marked as paid and the customer receives a receipt by e-mail. | Must | Kick-off states the system must integrate with Vipps; the owner insists on it. | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_owner_2026-08-14.txt [Q3]: "Vipps for private customers, definitely." 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 2]: "Must integrate with Fiken (accounting) and Vipps (payments)." 04_dataset_customer-emails_2026-10-20.csv [E009]: "Kan jeg betale med Vipps for bursdag 30 pers? Og kan jeg få kvittering på e-post?" [translation: Can I pay with Vipps for a birthday party of 30? And can I get a receipt by e-mail?] | DIRECT | Vipps agreement and API details are external dependencies (ISS-09). The e-mail receipt is from one customer request.
US-22 | EP-04 | Payments and invoicing | As the owner, I want a deposit to be required for defined booking types so that no-shows are reduced. | AC1: Given a booking of a type that requires a deposit, when the booking is made, then a deposit request is issued and the booking stays unconfirmed until it is paid. [Only one AC is supported by the evidence; further criteria need PO input.] | Should | Scope is in conflict (all bookings vs weddings only); priority depends on the PO decision. | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | 01_interview_owner_2026-08-14.txt [Q2]: "I want the system to take a 30 % deposit when someone books - no deposit, no booking." 01_interview_event-coordinator_2026-08-15.txt [Q3]: "Honestly, corporate clients hate prepayment." 01_interview_event-coordinator_2026-08-15.txt [Q3]: "For weddings a deposit makes sense." 01_interview_corporate-customer_2026-08-19.txt [Q3]: "We cannot prepay, our finance department does not allow it." 02_process_as-is-order-handling_2026-08-15.md [step 6]: "For weddings, the coordinator sends a Vipps payment request for a deposit (sometimes forgotten)." | UNRESOLVED | PO REVIEW: see ISS-01. Likely Must for weddings if scope is confirmed: wedding bookings for May 2027 will be made before go-live. Refund rules are not documented.
US-23 | EP-04 | Payments and invoicing | As a corporate customer, I want one EHF invoice per month with my reference (cost centre or PO number) on each line so that our finance department can process it. | AC1: Given a corporate customer on monthly invoicing, when the month is closed, then one EHF invoice containing all that month's orders is produced. AC2: Given an order has a customer reference, when the invoice is produced, then the reference appears on that invoice line. | Must | Corporate customers cannot prepay and reject PDF invoices; losing them is a documented risk. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv 03_Architecture/03_landscape_current-it_2026-10-20.txt | 01_interview_corporate-customer_2026-08-19.txt [Q3]: "One EHF invoice per month, with our cost-centre code on each line." 01_interview_event-coordinator_2026-08-15.txt [Q3]: "Fjordtek and the other big firms want one invoice per month with all their lunches on it, sent as EHF." 04_dataset_customer-emails_2026-10-20.csv [E004]: "our finance department only accepts EHF invoices with our PO number. Last invoice was a PDF by e-mail and was rejected." 04_dataset_customer-emails_2026-10-20.csv [E016]: "Can we have separate logins but one monthly invoice?" 03_landscape_current-it_2026-10-20.txt [Accounting]: "Fiken (has a REST API; supports EHF invoices)" | DIRECT | PO REVIEW: Must is INFERRED from the documented risk of losing corporate customers. Different customers use different references (cost centre vs PO number).
US-24 | EP-04 | Payments and invoicing | As the owner, I want invoices for orders to be created in Fiken from the order data so that the coordinator no longer creates invoices manually. | AC1: Given an order is completed and invoiced, when the invoice is created, then it appears in Fiken with the order lines. AC2: Given an invoice created through the system, when it is viewed in Fiken, then it can be traced to its order number. | Must | Kick-off states the system must integrate with Fiken; the owner will not change accounting system. | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 01_Requirements/sources/01_interview_owner_2026-08-14.txt 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 2]: "Must integrate with Fiken (accounting) and Vipps (payments)." 01_interview_owner_2026-08-14.txt [Q3]: "We use Fiken for accounting today and I do not want to change that." 02_process_as-is-order-handling_2026-08-15.md [step 11]: "After the event the coordinator creates an invoice in Fiken manually" 02_process_as-is-order-handling_2026-08-15.md [step 12]: "Once a month the owner reconciles Fiken with the Excel sheet." | DIRECT | Fiken API coverage (invoice creation, payment status) must be confirmed (ISS-05). The traceability AC is an ASSUMPTION.
US-25 | EP-05 | Corporate customer accounts | As a corporate customer, I want a company account where several colleagues can log in and order so that we do not depend on one person sending e-mails. | AC1: Given a company account with several users, when any user places an order, then the order is linked to the company account. AC2: Given a user of the company account logs in, when they open the order list, then they see the company's orders, including standing orders. | Should | Valuable for the largest customer segment; e-mail/coordinator entry still works at go-live. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "A login for our company where I can see our standing orders" 01_interview_corporate-customer_2026-08-19.txt [Q2]: "Several of my colleagues should be able to order" 04_dataset_customer-emails_2026-10-20.csv [E016]: "Three of us order lunches for different departments. Can we have separate logins but one monthly invoice?" | DIRECT | User administration (who adds users) and visibility between departments are not documented.
US-26 | EP-05 | Corporate customer accounts | As a corporate customer's office manager, I want orders above 15 000 NOK to require my approval so that large spending is controlled. | AC1: Given a user who is not the approver places an order above 15 000 NOK, when it is submitted, then it stays pending until the approver approves it. AC2: Given an order of 15 000 NOK or less, when it is submitted, then no approval is required. | Could | One customer's internal control rule; not linked to go-live needs. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "only I should approve anything above 15 000 NOK." | DIRECT | PO REVIEW: confirm whether the threshold is per customer and configurable (ISS-08). Whether 'above' includes VAT is unknown.
US-27 | EP-05 | Corporate customer accounts | As a corporate customer, I want to set up standing (recurring) orders so that I do not have to e-mail the same order every week. | AC1: Given a weekly standing order, when a new week starts, then an order for that week is created with the standing quantities. AC2: Given a company user logs in, when they open standing orders, then all active standing orders are listed. | Should | Repeatedly requested by corporate customers; can be handled manually at go-live. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "see our standing orders" 01_interview_corporate-customer_2026-08-19.txt [Q1]: "I send an e-mail every Thursday with next week's lunch meetings." 04_dataset_customer-emails_2026-10-20.csv [E007]: "Could we set up a standing order: lunch for 12 every Tuesday, vegetarian option for 3?" | DIRECT | How far ahead standing orders are generated and how exceptions (holidays) are handled is not documented.
US-28 | EP-05 | Corporate customer accounts | As a returning customer, I want to copy a previous order so that I can reorder without re-entering the details. | AC1: Given a previous order, when the customer chooses to copy it, then a new draft order with the same items and guest groups is created for a new date. [Only one AC is supported by the evidence; further criteria need PO input.] | Should | Requested by two independent sources; not a go-live condition. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "copy last week's order" 04_dataset_customer-emails_2026-10-20.csv [E028]: "Could we just get exactly the same as our order in September? I don't have the details anymore." | DIRECT | Behaviour when a copied dish is no longer on the seasonal menu is not documented.
US-29 | EP-05 | Corporate customer accounts | As a corporate customer, I want our accountant to have read-only access to our invoices and order history so that they can check them without asking us. | AC1: Given a user with read-only access, when they log in, then they can view invoices and order history but cannot create or change orders. [Only one AC is supported by the evidence; further criteria need PO input.] | Could | Single request; low urgency. | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E029]: "Can our accountant get read-only access to our invoices and order history?" | DIRECT | Depends on US-25 (company accounts).
US-30 | EP-06 | Privacy and data-subject rights | As a customer, I want to request access to the personal data Ekte Mat holds about me so that I can see what is stored. | AC1: Given a customer submits an access request, when the coordinator processes it, then the customer's personal data held in the system can be exported for the customer. [Only one AC is supported by the evidence; further criteria need PO input.] | Must | Documented obligation in the GDPR advice; applies from go-live because personal data is stored from day one. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 3]: "Customers must be able to request access and deletion." | DIRECT | Response deadline and identity verification are not documented (ISS-16). The export mechanism in the AC is an ASSUMPTION.
US-31 | EP-06 | Privacy and data-subject rights | As a customer, I want my personal data to be deleted when I ask, or when my company stops being a customer, so that my privacy is respected. | AC1: Given a deletion request, when it is processed, then the customer's personal data is deleted except data that must be kept for bookkeeping, and the customer receives a confirmation. AC2: Given a corporate customer relationship ends, when the deletion process runs, then the names of that company's employees are deleted. | Must | Documented obligation in the GDPR advice and a corporate customer requirement. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 3]: "Customers must be able to request access and deletion." 01_note_gdpr-consultant_2026-08-20.txt [bullet 2]: "Keep order data needed for bookkeeping 5 years (Norwegian Bookkeeping Act)" 04_dataset_customer-emails_2026-10-20.csv [E010]: "Please delete all personal data you have about me and confirm by e-mail." 01_interview_corporate-customer_2026-08-19.txt [Q4]: "they want to know that you delete our employees' names when we stop being a customer." | DIRECT | Deletion deadlines are missing (NFR-08, ISS-07). E010 is a real pending request in the current process; it is outside the system scope but should be handled now.

## Non-functional requirements
Requirement ID | Quality Characteristic | Requirement Statement | Metric | Target Value | Unit | Measurement Conditions/Verification Method | Source File(s) | Supporting Quote | Evidence Status | Assumptions/Unresolved Details
NFR-01 | Performance efficiency (time behaviour) | Customer-facing pages shall load fast enough not to deter customers. CANDIDATE: no target agreed. | Page load time | TBC (not agreed) | s | To be defined once a target and test conditions (device, network, page set) are agreed. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q4]: "Please do not make it slow. The old booking plugin on the website took ten seconds to load a page." | UNRESOLVED | 10 s is the unacceptable baseline, not a target. Question in ISS-10.
NFR-02 | Availability | Customers shall be able to view menus and send booking requests at any hour. CANDIDATE: availability target missing. | Availability of menu and booking functions | TBC (not agreed) | % per month | To be defined: measurement period, maintenance windows, monitoring method. | 01_Requirements/sources/01_interview_owner_2026-08-14.txt | 01_interview_owner_2026-08-14.txt [Q2]: "send a booking request themselves, at any hour." | UNRESOLVED | 'At any hour' gives no numeric target. Question in ISS-11.
NFR-03 | Reliability (fault tolerance) | The kitchen view shall still show today's orders during an internet outage. | Today's orders viewable on the kitchen device with the network disconnected | All of today's orders as of the last successful update | orders | Test: load the kitchen view, disconnect the network, verify that all of today's orders remain visible. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q3]: "It happened twice last winter. The kitchen must still see today's orders. Printing works too, but the screen should not just go blank." | DIRECT | Acceptable data age and whether changes are possible offline are not documented.
NFR-04 | Security / privacy (data residency) | Personal data shall be stored and processed only in the EU/EEA. | Share of personal data stored or processed in the EU/EEA | 100 | % | Review of hosting locations and sub-processors listed in each provider's data processing agreement. | 03_Architecture/03_landscape_current-it_2026-10-20.txt 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 03_landscape_current-it_2026-10-20.txt [Constraints]: "data must stay in EU/EEA (GDPR)" 01_interview_corporate-customer_2026-08-19.txt [Q4]: "They want it in the EU/EEA" | DIRECT | 100 % follows from 'must stay'. Not a claim of legal compliance.
NFR-05 | Privacy (data minimisation) | Allergy and dietary information shall be stored per guest group, not per named guest, unless strictly needed. | Data fields linking allergy or diet data to a named guest | 0 (unless a documented exception exists) | fields | Data-model review before release. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 1]: "Allergy and dietary information about named persons can be health data (special category, GDPR art. 9). Store per guest group, not per named guest, unless strictly needed." | DIRECT | Expressing this as a field count is an interpretation. 'Strictly needed' exceptions are undefined.
NFR-06 | Privacy (retention) | Order data needed for bookkeeping shall be kept for 5 years. | Retention period for bookkeeping order data | 5 | years | Review of retention configuration; test that bookkeeping data survives a deletion request. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 2]: "Keep order data needed for bookkeeping 5 years (Norwegian Bookkeeping Act)" | DIRECT | Based on a phone note from the consultant; not legally verified here. Start of the period and the exact fields are undefined.
NFR-07 | Privacy (retention) | Personal data not needed for bookkeeping shall have a shorter retention period. CANDIDATE: period missing. | Retention period for other personal data | TBC (shorter than 5 years) | months | To be defined. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 2]: "other personal data should have a shorter retention period." | UNRESOLVED | Retention period not stated. Question in ISS-07.
NFR-08 | Privacy (deletion) | Employee names of a corporate customer shall be deleted when the customer relationship ends. CANDIDATE: deadline missing. | Time from end of customer relationship to deletion | TBC (not agreed) | days | To be defined. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_corporate-customer_2026-08-19.txt [Q4]: "they want to know that you delete our employees' names when we stop being a customer." | UNRESOLVED | Deadline and the definition of 'stop being a customer' are missing. Question in ISS-07.
NFR-09 | Security / compliance (contracts) | A data processing agreement shall exist with every cloud or SaaS provider that processes personal data. | Share of such providers with a signed data processing agreement | 100 | % | Contract register check before go-live. | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 4]: "A data processing agreement is needed with any cloud/SaaS provider." | DIRECT | Applies to Vipps, Fiken, hosting and e-mail providers as relevant (INFERRED).
NFR-10 | Usability (localisation) | The user interface shall be available in Norwegian and English. | Supported UI languages | 2 (Norwegian, English) | languages | Review of all customer-facing screens in both languages. | 03_Architecture/03_landscape_current-it_2026-10-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 03_landscape_current-it_2026-10-20.txt [Constraints]: "Norwegian and English UI." 04_dataset_customer-emails_2026-10-20.csv [E012]: "Is your menu available in English with allergens marked?" | DIRECT | Scope (customer-facing only, or also kitchen and admin views) is unresolved (ISS-19).
NFR-11 | Cost (operational constraint) | Running costs of the solution shall stay below 3 000 NOK per month. | Monthly running cost | < 3 000 | NOK/month | Sum of monthly hosting, licence and SaaS invoices after go-live. | 00_Project_management/00_plan_budget-and-constraints_2026-10-20.txt 03_Architecture/03_landscape_current-it_2026-10-20.txt | 00_plan_budget-and-constraints_2026-10-20.txt [Running cost]: "Running cost target: < 3 000 NOK/month" 03_landscape_current-it_2026-10-20.txt [Constraints]: "prefer low running cost (< 3 000 NOK/month)" | DIRECT | Project constraint rather than a product quality. Whether transaction fees (e.g. Vipps) count is not documented.
NFR-12 | Maintainability / operability | Day-to-day content (e.g. menus) shall be manageable by non-technical staff. CANDIDATE: no measurable target. | TBC | TBC (not agreed) | TBC | To be defined, e.g. through a usability test with staff once tasks and criteria are agreed. | 03_Architecture/03_landscape_current-it_2026-10-20.txt 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 03_landscape_current-it_2026-10-20.txt [Constraints]: "nobody technical in-house" 01_interview_head-chef_2026-08-15.txt [Q2]: "I want to edit the menu myself" | UNRESOLVED | No metric or threshold is documented.
NFR-13 | Compatibility | The kitchen view shall run on a wall-mounted tablet. | Supported kitchen device | TBC (device and OS not specified) | device | Test on the selected device. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt 03_Architecture/03_landscape_current-it_2026-10-20.txt | 01_interview_head-chef_2026-08-15.txt [Q1]: "Tablet on the wall." 03_landscape_current-it_2026-10-20.txt [Kitchen]: "one old iPad nobody uses" | INFERRED | Whether the existing iPad should be reused is not stated.

## Conflicts and open questions
Issue ID | Issue Type | Topic | Description | Stakeholder/Source A and Position | Stakeholder/Source B and Position | Source File(s) | Supporting Quote/Evidence | Potential Impact | Specific Product-Owner Question | Decision Owner (if evidenced) | Status
ISS-01 | Conflict | Deposit / prepayment | The owner wants a 30 % deposit on every booking; the event coordinator and the corporate customer say corporate customers cannot or will not prepay. | Owner (01_interview_owner): 30 % deposit for every booking, 'no deposit, no booking'. | Event coordinator and corporate customer: no prepayment for corporate customers; deposit acceptable for weddings. | 01_Requirements/sources/01_interview_owner_2026-08-14.txt 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_owner_2026-08-14.txt [Q2]: "I want the system to take a 30 % deposit when someone books - no deposit, no booking." 01_interview_event-coordinator_2026-08-15.txt [Q3]: "If we force a deposit on them, we will lose them. For weddings a deposit makes sense." 01_interview_corporate-customer_2026-08-19.txt [Q3]: "We cannot prepay, our finance department does not allow it." | Affects US-22 and US-23. Risk of losing corporate customers, or of continued no-shows. | Which booking types require the 30 % deposit: (a) all, (b) weddings only, (c) all except corporate customers on monthly invoicing? What are the refund rules? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-02 | Open Question | Build vs buy | Kick-off left open whether to build a custom system or configure a catering SaaS. | Kick-off minutes: open question. | - | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 8]: "Open question: build our own system or configure an off-the-shelf catering SaaS?" | Affects architecture, cost (NFR-11), data processing agreements (NFR-09) and all stories. | Will the team build its own system or configure a catering SaaS? By which sprint must this be decided? | Not evidenced | Open
ISS-03 | Open Question | Order change deadline | No company-wide deadline for customer changes exists. One customer wants changes until 10:00 the day before; the vision says 'change orders any time'. | Corporate customer: changes until 10:00 the day before. | Vision draft v0.3: 'book and change orders any time'. | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "change the number of people until 10:00 the day before" 01_vision_draft-v0.3_2026-10-20.docx [para 1]: "book and change orders any time" | Affects US-11 and kitchen planning. | What is the latest time a customer may change guest numbers or allergies, and does it differ for lunches and events? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-04 | Missing Evidence | Cancellation terms | A customer asks for cancellation terms; none are documented. | Customer e-mail E013: asks for terms. | - | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E013]: "What are your cancellation terms?" | US-13 cannot be fully specified. | What are the cancellation deadlines and fees for each booking type? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-05 | Dependency | Fiken and EHF | Invoice creation, EHF sending and payment-status updates depend on Fiken's API. A customer received a wrong payment reminder. | IT landscape: Fiken has a REST API and supports EHF. | Customer e-mail E030: wrong payment reminder. | 03_Architecture/03_landscape_current-it_2026-10-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 03_landscape_current-it_2026-10-20.txt [Accounting]: "Fiken (has a REST API; supports EHF invoices)" 04_dataset_customer-emails_2026-10-20.csv [E030]: "We received a payment reminder for an invoice we paid on 2 Sept." | Affects US-23 and US-24. | Can the team get test access to Fiken's API, and should payment status be read back from Fiken into the system? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-06 | Open Question | Capacity rule | Capacity is described as 'about 400 covers a day, 250 if there is a wedding with a served dinner'. It is unclear whether this is a hard limit or a warning. | Event coordinator: approximate limits. | - | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt | 01_interview_event-coordinator_2026-08-15.txt [Q4]: "Our kitchen can do about 400 covers a day, 250 if there is a wedding with a served dinner." | Affects US-03 and US-10. | Are 400 and 250 covers per day hard limits that block bookings, or warnings to the coordinator? Who may override them? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-07 | Missing Evidence | Retention and deletion periods | Retention for non-bookkeeping personal data and deadlines for deletion are not stated. | GDPR note: 'shorter retention period' (no value). | Corporate customer: deletion at end of relationship (no deadline). | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 2]: "other personal data should have a shorter retention period." 01_interview_corporate-customer_2026-08-19.txt [Q4]: "delete our employees' names when we stop being a customer." | NFR-07 and NFR-08 cannot be tested; affects US-31. | What retention period applies to personal data not needed for bookkeeping, and within how many days must data be deleted after a request or end of relationship? | Not evidenced | Open
ISS-08 | Open Question | Approval threshold | One customer wants approval above 15 000 NOK. It is unclear whether thresholds are per customer and configurable. | Corporate customer: only the office manager approves orders above 15 000 NOK. | - | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | 01_interview_corporate-customer_2026-08-19.txt [Q2]: "only I should approve anything above 15 000 NOK." | Affects US-26. | Should approval thresholds be configurable per company account, and is the amount incl. or excl. VAT? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-09 | Dependency | Vipps integration | Vipps payments depend on an agreement and API access that are not documented. | Kick-off: must integrate with Vipps. | - | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 2]: "Must integrate with Fiken (accounting) and Vipps (payments)." | Affects US-21 and US-22. | Does Ekte Mat have a Vipps merchant agreement that allows API integration, and who will request test access? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-10 | Missing Evidence | Performance target | Speed is a stated need, but no target is given. | Head chef: 'do not make it slow'. | - | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q4]: "Please do not make it slow." | NFR-01 cannot be tested. | What is the maximum acceptable page load time, on which device and network? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-11 | Missing Evidence | Availability target | 'At any hour' has no numeric availability target. | Owner: booking at any hour. | - | 01_Requirements/sources/01_interview_owner_2026-08-14.txt | 01_interview_owner_2026-08-14.txt [Q2]: "at any hour." | NFR-02 cannot be tested; affects hosting choice and cost. | What monthly availability (%) is required for menus and booking, and are planned maintenance windows acceptable? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-12 | Open Question | Phone ordering | Phone orders are part of today's process and a customer asks if phone ordering continues. | As-is process: phone calls noted on paper. | Customer e-mail E024: asks to keep ordering by phone. | 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 04_Data/04_dataset_customer-emails_2026-10-20.csv | 02_process_as-is-order-handling_2026-08-15.md [step 1]: "Customer sends an e-mail or calls (phone calls are noted on paper)." 04_dataset_customer-emails_2026-10-20.csv [E024]: "Kan jeg fortsatt bestille på telefon?" [translation: Can I still order by phone?] | Affects US-09 and the scope of the coordinator's role. | Will phone and e-mail orders still be accepted after go-live, with the coordinator entering them in the system? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-13 | Missing Evidence | Driver needs | The driver is part of the process but was not interviewed. | As-is process / IT landscape: driver uses printouts and own phone. | - | 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md 03_Architecture/03_landscape_current-it_2026-10-20.txt | 02_process_as-is-order-handling_2026-08-15.md [step 10]: "Driver gets the address from the printout." 03_landscape_current-it_2026-10-20.txt [Driver]: "Driver: own phone, Google Maps" | Delivery stories may be incomplete (US-14). | Should the team interview the driver before Sprint 2, and does the driver need access to the system? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-14 | Open Question | Kitchen PIN vs health data | A PIN login is requested for the kitchen tablet, which will display allergy data that may be health data. | Head chef: PIN is fine. | GDPR note: allergy data about named persons can be health data. | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_interview_head-chef_2026-08-15.txt [Q1]: "a PIN is fine." 01_note_gdpr-consultant_2026-08-20.txt [bullet 1]: "Allergy and dietary information about named persons can be health data" | Affects US-17 and NFR-05. Not a conflict if allergy data is stored per guest group. | Is a shared or personal PIN acceptable for the kitchen tablet, given that it shows allergy information per guest group? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-15 | Missing Evidence | Recipe quantities | A prep list in kilos requires ingredient quantities per portion, which are not in the evidence. | Head chef: prep list in kilos. | - | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | 01_interview_head-chef_2026-08-15.txt [Q2]: "total kilos of each ingredient for the next three days." | US-20 cannot be implemented without recipe data. | Who will provide ingredient quantities per portion for each dish, and in what format? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-16 | Missing Evidence | Data-subject request handling | Deadline and identity checks for access and deletion requests are not documented. A deletion request (E010) is already pending. | GDPR note: customers must be able to request access and deletion. | - | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt 04_Data/04_dataset_customer-emails_2026-10-20.csv | 01_note_gdpr-consultant_2026-08-20.txt [bullet 3]: "Customers must be able to request access and deletion." 04_dataset_customer-emails_2026-10-20.csv [E010]: "Please delete all personal data you have about me and confirm by e-mail." | Affects US-30 and US-31. | Who handles access and deletion requests, how is identity verified, and what response deadline applies? Has request E010 been handled? | Not evidenced | Open
ISS-17 | Missing Evidence | Pricing rules | Customers ask about volume discounts and a children's menu; no pricing rules are documented. | Customer e-mail E020: discount above 150 guests. | Customer e-mail E027: children's menu. | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E020]: "Do you have a discount above 150 guests?" 04_dataset_customer-emails_2026-10-20.csv [E027]: "Do you have a children's menu?" | Affects price display (US-01) and quotes. | Are there volume discounts or special menus (e.g. children) that the system must calculate or display? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-18 | Missing Evidence | Accessibility | No accessibility requirement or standard is documented. An elderly customer prefers phone ordering. | Customer e-mail E024. | - | 04_Data/04_dataset_customer-emails_2026-10-20.csv | 04_dataset_customer-emails_2026-10-20.csv [E024]: "Jeg er 82 år og bruker ikke internett så mye." [translation: I am 82 and do not use the internet much.] | No accessibility NFR could be written. | Must the customer-facing website meet a specific accessibility standard (e.g. WCAG level)? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-19 | Open Question | Language scope | Norwegian and English UI is required, but the scope is not defined. | IT landscape: Norwegian and English UI. | - | 03_Architecture/03_landscape_current-it_2026-10-20.txt | 03_landscape_current-it_2026-10-20.txt [Constraints]: "Norwegian and English UI." | Affects NFR-10 and effort. | Must kitchen and admin screens also be available in both languages, or only customer-facing pages and menus? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-20 | Open Question | Go-live meaning | Sources describe 2027-03-01 as a 'soft launch target' and as a 'hard' go-live. Whether a soft launch allows a reduced scope is unclear. | Kick-off minutes: soft launch target. | Budget note: go-live hard. | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt 00_Project_management/00_plan_budget-and-constraints_2026-10-20.txt | 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 4]: "Soft launch target: 1 March 2027." 00_plan_budget-and-constraints_2026-10-20.txt [Go-live]: "Go-live: 1 March 2027 (hard)" | Determines which stories are Must. | Is 2027-03-01 a hard date for the full Must scope, or a soft launch with a limited customer group? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-21 | Open Question | Existing tools | It is unclear whether the new system replaces the Wix website and the Google Calendar capacity check, or integrates with them. | IT landscape: Wix website, Google Workspace. | - | 03_Architecture/03_landscape_current-it_2026-10-20.txt 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | 03_landscape_current-it_2026-10-20.txt [Website]: "Website: Wix, 6 pages, contact form -> sends e-mail to post@ektemat.example" 00_minutes_kickoff-meeting_2026-08-12.txt [bullet 2]: "Google Workspace used for e-mail/calendar" | Affects architecture and US-02, US-10. | Will the new system replace the Wix website and the Google Calendar capacity check, or must it integrate with them? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-22 | Open Question | Scope vs budget | The Must scope (11 stories) has not been estimated against the 450 000 NOK budget and the go-live date. | Budget note. | - | 00_Project_management/00_plan_budget-and-constraints_2026-10-20.txt | 00_plan_budget-and-constraints_2026-10-20.txt [Budget]: "Budget first version: 450 000 NOK incl. 12 months hosting" | Risk that the Must scope does not fit. | After estimation, which Must stories may be moved to Should if the scope exceeds budget or time? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-23 | Open Question | Small epic | EP-06 (Privacy and data-subject rights) has only 2 stories, below the 3-story guideline. No stories were invented to fill it. | Backlog rule: 3-8 stories per epic. | - | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [bullet 3]: "Customers must be able to request access and deletion." | Backlog structure only. | Keep EP-06 as a small compliance epic, or merge its stories into another epic? | Ingrid Solheim (product owner, per 00_minutes bullet 5) | Open
ISS-24 | Missing Evidence | GDPR advice verification | GDPR obligations come from a phone note, not a written legal assessment. | GDPR note header: phone call. | - | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | 01_note_gdpr-consultant_2026-08-20.txt [header]: "Note from data-protection consultant (phone call, 20 Aug 2026)" | Risk of building on unverified legal assumptions (NFR-04 to NFR-09). | Can the consultant confirm the advice in writing, including the 5-year bookkeeping retention? | Not evidenced | Open
AUDIT TRAIL (separate from the issue table above)
Inspected 2026-10-22. Story counts are live formulas over the 'User stories' Source File(s) column.
# | File | Relative Path (from EkteMat_repo) | File Type | Read Successfully | Contributed Stories | Distinct Stories Supported | Other Contribution | Notes / Exclusion Reason
1 | 01_interview_owner_2026-08-14.txt | 01_Requirements/sources/01_interview_owner_2026-08-14.txt | txt | Yes | Yes | 7 | Stakeholders, NFR-02, issues
2 | 01_interview_event-coordinator_2026-08-15.txt | 01_Requirements/sources/01_interview_event-coordinator_2026-08-15.txt | txt | Yes | Yes | 7 | Stakeholders, issues
3 | 01_interview_head-chef_2026-08-15.txt | 01_Requirements/sources/01_interview_head-chef_2026-08-15.txt | txt | Yes | Yes | 5 | NFR-01, 03, 12, 13; issues
4 | 01_interview_corporate-customer_2026-08-19.txt | 01_Requirements/sources/01_interview_corporate-customer_2026-08-19.txt | txt | Yes | Yes | 9 | NFR-04, 08; issues
5 | 01_note_gdpr-consultant_2026-08-20.txt | 01_Requirements/sources/01_note_gdpr-consultant_2026-08-20.txt | txt | Yes | Yes | 3 | NFR-05 to 09; issues | Advice from a phone note; not legally verified.
6 | 01_vision_draft-v0.3_2026-10-20.docx | 01_Requirements/sources/01_vision_draft-v0.3_2026-10-20.docx | docx | Yes | Yes | 4 | Issues | Text read from paragraphs; no tables or images found.
7 | 00_minutes_kickoff-meeting_2026-08-12.txt | 00_Project_management/00_minutes_kickoff-meeting_2026-08-12.txt | txt | Yes | Yes | 3 | Stakeholders, issues | Expected input; located in 00_Project_management, not in sources/.
8 | 00_plan_budget-and-constraints_2026-10-20.txt | 00_Project_management/00_plan_budget-and-constraints_2026-10-20.txt | txt | Yes | No | 0 | NFR-11, issues | Expected input; located in 00_Project_management. No functional stories: content is constraints only.
9 | 02_process_as-is-order-handling_2026-08-15.md | 02_Analysis_and_models/02_process_as-is-order-handling_2026-08-15.md | md | Yes | Yes | 8 | Stakeholders, issues | Expected input; located in 02_Analysis_and_models.
10 | 03_landscape_current-it_2026-10-20.txt | 03_Architecture/03_landscape_current-it_2026-10-20.txt | txt | Yes | Yes | 2 | NFR-04, 10-13; issues | Expected input; located in 03_Architecture.
11 | 04_dataset_customer-emails_2026-10-20.csv | 04_Data/04_dataset_customer-emails_2026-10-20.csv | csv | Yes | Yes | 21 | Stakeholders, NFR-10, issues | Expected input; located in 04_Data. 30 records; columns email_id, received, from_name, from_address, subject, body, language. Cited by email_id; names and addresses not reproduced. Records used: see note below.
12 | 04_reference_lunch-menu-autumn_2026-10-20.txt | 04_Data/04_reference_lunch-menu-autumn_2026-10-20.txt | txt | Yes | Yes | 1 | - | Reference material (allergen list). Not in the expected-input list; included because it supports US-06.
13 | 04_dataset_orders-2024-2025_2026-09-27.xlsx | 04_Data/04_dataset_orders-2024-2025_2026-09-27.xlsx | xlsx | Partially (headers only) | No | 0 | - | Historical order data; not a requirements source in the brief. Not analysed for stories.
14 | 02_benchmark_competitor-links_2026-10-20.txt | 02_Analysis_and_models/02_benchmark_competitor-links_2026-10-20.txt | txt | Yes | No | 0 | - | Excluded: competitor links for benchmarking only; external sites not opened (no research authorised).
15 | 00_todo_sprint0-setup_2026-10-20.txt | 00_Project_management/00_todo_sprint0-setup_2026-10-20.txt | txt | Yes | No | 0 | - | Excluded: team to-do, no requirements content.
16 | 99_note_logo-ideas_2026-10-20.txt | 99_Not_relevant/99_note_logo-ideas_2026-10-20.txt | txt | Yes | No | 0 | - | Excluded: marked not relevant to system development.
17 | README.md | README.md | md | Yes | No | 0 | - | Excluded: repository index written by the team.
| Total unique user stories |  |  |  |  | 31
| Sum of per-file story counts |  |  |  |  | 70
| Note | The sum exceeds the unique total because one story can be supported by several files. CSV records supporting stories: E001, E002, E003, E004, E005, E006, E007, E008, E009, E010, E011, E012, E013, E014, E015, E016, E017, E018, E019, E021, E022, E023, E024, E028, E029. Records used only for stakeholders/NFRs/issues: E020, E025, E027, E030. Records with no requirement content (not used): E026. No story is classified Won't: no source explicitly excludes or defers a need. Originals in EkteMat_project_inbox were not re-read; the repo copies are SHA-256-identical (verified 2026-10-22). The inbox file 'Kopi av interview Sunniva (2).txt' is an exact duplicate of the event-coordinator interview and was not counted.